## Sheet1
Schedule Tracking Metrics
Iteration | S/N | Task | Estimated Duration (days) | Actual Duration (days) | Score(%) | Severity | Comment
1
load factor
= 4 hours
Overall Score |  |  |  |  | #DIV/0!
Iteration | S/N | Task | Estimated Duration (days) | Actual Duration (days) | Score(%) | Severity | Comment
2 | 1
load factor | 2
= 4 hours | 3
4
5
6
7
8
9
10
11
12
13
14
<First Milestone :
Overall Score |  |  |  |  | 0%
Iteration | S/N | Task | Estimated Duration (days) | Actual Duration (days) | Score(%) | Severity | Severity
3 | 1
load factor | 2
= 6 hours | 3
4
5
6
7
8
<Second Milestone :
Overall Score
Iteration | S/N | Task | Estimated Duration (days) | Actual Duration (days) | Score(%) | Severity | Severity
4 | 1
load factor | 2
= 6 hours | 3
4
5
<Third Milestone:
Overall Score
Iteration | S/N | Task | Estimated Duration (days) | Actual Duration (days) | Score(%) | Severity | Severity
5 | 1
load factor | 2
= 6 hours | 3
4
5
<Fourth Milestone:
Overall Score
Score |  | Action
SM < 50 |  | 1. Immediately, inform your supervisor about the slip within 24 hours. 2. Then use the same mitigation as the category 50 < SM < 90 and seriously consider dropping tasks.
50 < SM <= 90 |  | 1. Re-estimate the tasks for the future iterations. 2. Deduct the number of days behind schedule from buffer days. 3. If there is no more buffer day, decide the functionalities to drop.
90 < SM <= 110 |  | Our estimates are fairly accurate, and we are roughly on track. 1. Add/Deduct the number of days behind schedule from buffer days. 2. If there is no more buffer day, decide the functionalities to drop
110 < SM <= 150 |  | Gross over-estimated the effort required. 1. Re-estimate the tasks for the future iterations. 2. Add the number of days gained to buffer days
150 < SM |  | 1. Immediately, inform your supervisor about the slip within 24 hours. 2. Then use the same mitigation as the category 110 < SM < 150